| ## Date and Time: | 13th January 2026 ¦ 8.00am – 9.30am |
| --- | --- |
| Venue: | Springfield City Group, Springfield Tower, 145 Sinnathamby Blvd, Springfield Central |
| Chairperson: | Rohan Richarson – Managing Director & CEO, Future Forgeworks Rees Banks - Chief Executive Officer, Regional Development Australia Ipswich & West Moreton Inc Dr Richard Eden – Executive General Manager, Education and Smart City, Springfield City Group Sarah Prest – Principal Economic Development Officer, Department of State Development and Infrastructure Neil Coupland – President, Greater Springfield Chamber of Commerce Rouz Fard– Head, Industry & Community Partnerships, Uni SQ Tom Rowe– Executive Director, Education and Training, TAFE Queensland South West Dan Heenan - Economic Development Manager, Office of the General Manager - ICC Glen Watson – Regional Director Department of Trade, Employment and Training Paul Clarkson- Director, Recruitment Workforce Planning & Analytics, Mater Jeril Thomas – Regional Manager, Multicultural Australia Alfio Balsamo – Dean of College, WesTEC CEO Sarah-Jane Gourley – Manager, Regional School Industry Partnerships Program, Department of Education Elisabeth Rung – Centre Manager, Mirvac Orion Springfield Central Steve Cunliffe – Engagement Manager Regional Brisbane, Construction Skills Queensland Elaine Wallace – Apprenticeships Manager, Boeing Defence Australia Ltd |
| Secretariat: | Liz Conroy – Project Manager |

| 1. Welcome and Open |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | Agenda & Discussion | Agreed Action | Action Officer | Required By |
| 1.1 | Welcome and Apologies - The meeting was opened 8.04am Tuesday, 13th January 2026, by R. Richardson - Acknowledgement of Country - Attendance and apologies - Welcome to Elaine Wallace, all look forward to her future contributions - Welcome Selena Turner (FFW), who is joining the meeting to meet and familiarise herself with the Committee. Selina will act as Rohan’s proxy when he is unavailable. | Apologies - Jeril Thomas - Sarah-Jane Gourley - Elaine Wallace | Rohan Richardson |  |
| 1.2 | Committee Member Terms of Reference and Update - Update of Terms of Reference to all Committee Members - Submitted to DTET for approval by required date of 30.11.2025 |  | Liz Conroy | 30.11.2025 |

| 2. Standing Agenda |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | Agenda & Discussion | Agreed Action | Action Officer | Required By |
| 2.1 | Confirmation of previous minutes - The minutes from the previous meeting held were accepted as a true and accurate. - R.Eden noted that we have lost the representation on the Committee of the largest high school in the region (SCSHS) and we should look at that in the future. | - Review SCSHS membership. | Rohan Richardson | All agreed |
| 2.2 | Declaration: Conflict of Interest - Nil | Updated Conflict of Interest Register has been distributed and is to be completed by each Committee Member | Liz Conroy | 31.12.2025 |
| 2.3 | Business from the Chair - Theme and focus for today’s meeting is for two things - The Action Plan - Working Group / Sub Committee Charter - The Action Plan is intended to be an evergreen document. While submission is due at the end of this month, the priority is to submit a plan that establishes early momentum and a clear framework for deliverables, with formal reviews every three months. The plan does not need to be 100 per cent complete at submission; it will be refined over time through ongoing industry engagement. The initial approach will focus on go and discover, followed by building and adapting actions as insights emerge. - The Sub-Committee Charter has been circulated. The intent of the group is to operate as a steering function, enabling broader and deeper industry engagement, rather than creating an additional layer of bureaucracy. Participation is voluntary and designed to remain flexible; accordingly, it is proposed that the group be referred to as a Working Group rather than a sub-committee. | - Action Plan is evergreen, reviewed every three months and determined by industry needs - Sub Committee is a Working Group | Rohan Richardson |  |
| 2.4 | Strategy Review from the Project Manager - Milestone dates - Action Plan to be submitted to DTET by 31 January 2026 - Stakeholder Engagement Map - Skilling and Training Assessment - Action Register Review | - First quarterly report and documents have been submitted to DTET - Skills and Training Assessment awaiting new date - Chair and PM to connect and update Greater Springfield, Ipswich and Centenary Chambers of Commerce at least quarterly - Chair and R Banks to attend Inala Study Hub Opening | Liz Conroy Rohan/Liz Rohan/Rees | 23.12.2025 ASAP 29.1.2026 |
| 2.5 | Committee Business - Establishment of the five Working Groups - Education – Lead Alfio Balsamo - Health – Lead Sarah-Jane Gourley - Trades – Steve confirmed his willingness to participate; however, he is unable to take on the lead role. Lead to be confirmed. - Services – Lead Elisabeth Rung - Economic/Cohort – Dan Heenan - Defence – Discussion held regarding the potential to merge the Defence and Trades groups. Further advice is to be sought from Ipswich City Council regarding the re-formation of the City of Ipswich Defence Industry Attraction Committee (CITADAC). - Action Plan discussion – Template supplied by DTET (shown on screen). Implement flexible, action-driven initiatives that extend the reach of the Committee to deepen industry engagement, capture direct industry insight, benchmark current workforce and operational needs, and identify key pain points to inform the development of targeted, locally-responsive solutions. - Industry Engagement – Rohan and Liz will commence outreach across the expanded region to engage directly with employers and industry representatives. This engagement will be used to identify current and emerging industry needs, inform place-based and industry-led workforce solutions, and build awareness that the SRJC is now operational across the region. Members are encouraged to share relevant industry contacts and, where possible, participate in meetings to support this outreach. - Jobs Portal – Expansion and Refinement: Agreement that the data and insights generated to date have been highly valuable; however, there is a need to improve visibility of end outcomes, including tracking placements and longer-term results where possible. - Skills Pathway Mapping – Investigate whether a current mechanism exists to inform parents and students about skills and career pathways; assess its currency, accessibility, and level of awareness; and determine whether a clear, one-page education brief, developed and updated annually by the Committee, could address industry-identified gaps and support informed pathway decisions. - Discussion Point: Investigate regional upskilling capacity and demand to assess whether current government-funded skills and training programs are aligned with local industry needs in terms of focus, scale, and skill level, and consider how insights can be systematically fed back to local, state, and federal governments to inform future skills investment and policy settings. | - Working Group Leads are to use the supplied Charter to establish group membership. - Leads are to report back to the SRJC on issues identified, along with proposed solutions and actions. - Working Groups are to be action-focused and outcomes-driven. - Groups to meet between SRJC Committee Meetings – set meeting before date by next meeting - Lead to determine group deliverables - D. Heenan to report on CITADAC - Undertake coordinated industry engagement across the expanded region to capture direct employer insight on workforce needs and challenges, enabling the SRJC to develop place-based, industry-informed solutions, while building awareness of the Committee’s operational role. - Investigate options to determine Jobs Portal end outcomes, including placements and longer-term results, without violating privacy requirements, while maintaining the integrity and usefulness of existing data and insights. - Investigate existing skills and career pathway information mechanisms for parents and students—including cadetships, apprenticeships, traineeships, and other education and training pathways—assessing currency, accessibility, and awareness, and determine whether development of a one-page education brief is an action required by the SRJC in response to industry-identified gaps. - Investigate regional upskilling needs and capacity to assess alignment between government-funded skills and training programs and current industry requirements, and determine appropriate mechanisms for feeding insights back to local, state, and federal governments to inform future skills investment and policy decisions. | WG Lead D.Heenan All All Liz Conroy / Rees Banks Education WG (Liz, Tom, Alfio, Richard, Glen) All | 3.2.2026 31.03.2026 ASAP Q1 2026 Q1 2026 Q2 2026 |

| 3.0 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | Agenda & Discussion | Agreed Action | Action Officer | Required By |
| 3.1 | - Springfield Jobs website portal (July 2025 – December 2025) - 386 - Jobs Advertised - 113 - Employers - 5,412 - Registered Job Seekers - 18,207 - Jobs Viewed - 854 - Jobs applied - 110,245 - Page Views - Springfield RJC Website (July – December 2025) - 8,242 – Views - Springfield RJC Facebook (July – December 2025) - 78 - Posts - 586,938 - Reaches - 7,864 – Followers Highlights since last meeting - Skills and training programs promoted - Lay the Way – Brick and Block Careers - Women in Construction – App QLD - Civil ready – Shadforth CSQ - Health Careers – Queensland Health - Construction Pathways - CSQ - MTA Institute Open Day - A decrease in engagement across communication channels was observed in December; however, this appears to be a consistent seasonal pattern following a significant increase in the preceding month. | All Committee Members to send communication or social media updates from their relevant sector to PM to share | Liz Conroy | Ongoing |
| 3.2 | Roundtable Discussion and Actions Arising Discussion: Develop a concise, one-page briefing script for Committee Members to use when introducing the expanded SRJC, clearly articulating its purpose, role, and priorities. | - Develop a concise, one-page briefing script for Committee Members to consistently introduce the expanded SRJC, clearly outlining its purpose, role, and key priorities. | Liz Conroy | Draft circulated by 22.1.2026 |

| 4. Close and Next Meeting |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | Agenda & Discussion | Agreed Action | Action Officer | Required By |
|  | Meeting Close - The meeting was closed by R Richardson at 9.43am - Next Meeting on Tuesday, 3rd February, 2026 |  |  |  |

| Attachments |  |
| --- | --- |
| Attachment # | Description |
| 1 | No attachments required as attachments are embedded in meeting minutes above. |

| Version Control |  |  |  |
| --- | --- | --- | --- |
| Version | Edited by | Date | Comments |
| 1.0 | Liz Conroy | 14/01/2026 |  |

Minute Authorisation:

______________________

Rohan Richardson

Chair

Springfield Regional Jobs Committee